## Test summary report
Tester | All team's member
Date | 14/12/2025

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Remove root admin succesfully | Can remove root admin | UC16 | Medium | Khoa | 14/12/2025 | Open
B002 | Error removing staff account | The system displays the "Delete successful" message without actually deleting the account | UC16 | Medium | Khoa | 14/12/2025 | Open
B003 | Cannot update role permission | When add new permission or removed permission for one role and click Save, new permission is not updated although message said successfully | UI17 | Medium | Khoa | 14/12/2025 | Open
B004 | No error message when circular dependency happens between categories | When editing parent category of specific one with its child category, although the system prevent, but there is no error message | UC13 | Low | Xuân Trường | 14/12/2025 | Open
B005 | Missing UI of how many products are in cart | After adding new product, in background it is put in the cart but the UI do not show how many products are inside | UC08 | Low | Khoa | 14/12/2025 | Closed
B006 | Sort option not triggering | When the admin apply a sorting option, the new list of products is not loaded unless the admin uses a filter. | UC12 | Low | Nhật Trường | 16/12/2025 | Open
B007 | Profile phone number missing validation | A user can update their phone number to include many types of input other than integers. | UC04 | Medium | Nhật Trường | 17/12/2025 | Open